## Sheet1
DRAWING REGISTER
Project No.: 11092
Project Name: FITZROY GASWORKS - PARCEL B
Project Address: 433 SMITH STREET FITZROY NORTH VIC 3068
Client: ASSEMBLE
Sheet No. | Sheet Name | Curr.Rev. | -/-/- | 23/05/25 | 23/06/25 | 01/08/25 | 08/08/25 | 03/09/25 | 12/09/25 | 18/03/26 | 24/03/26 | 08/04/26 | 23/04/26 | --- | 15/05/26 | 26/05/26
S0000 | DRAWING INDEX | B |  |  | A |  |  |  | B
S0001 | GENERAL NOTES - SHEET 1 | B |  |  | A |  |  |  | B
S0002 | GENERAL NOTES - SHEET 2 | B |  |  | A |  |  |  | B
S0101 | LOADING PLAN - BASEMENT 2 | A | [6 empty] | A
S0102 | LOADING PLAN - BASEMENT 1 | A | [6 empty] | A
S0103 | LOADING PLAN - GROUND | A | [6 empty] | A
S0104 | LOADING PLAN - MEZZANINE | A | [6 empty] | A
S0105 | LOADING PLAN - LEVEL 1 | A | [6 empty] | A
S0106 | LOADING PLAN - LEVEL 2 | A | [6 empty] | A
S0107 | LOADING PLAN - LEVEL 3 | A | [6 empty] | A
S0108 | LOADING PLAN - LEVEL 4 | A | [6 empty] | A
S0109 | LOADING PLAN - LEVEL 5 | A | [6 empty] | A
S0110 | LOADING PLAN - LEVEL 6 | A | [6 empty] | A
S0111 | LOADING PLAN - LEVEL 7 | A | [6 empty] | A
S0112 | LOADING PLAN - LEVEL 8 | A | [6 empty] | A
S0113 | LOADING PLAN - LEVEL 9 | A | [6 empty] | A
S0114 | LOADING PLAN - LEVEL 10 | A | [6 empty] | A
S0115 | LOADING PLAN - LEVEL 11 | A | [6 empty] | A
S0116 | LOADING PLAN - LEVEL 12 | A | [6 empty] | A
S0117 | LOADING PLAN - LEVEL 13 | A | [6 empty] | A
S0118 | LOADING PLAN - ROOF | A | [6 empty] | A
S1001 | SITE RETENTION AND BULK EXCAVATION PLAN | F |  |  | A | B | C | D | E | F
S1011 | SITE RETENTION ELEVATIONS - SHEET 1 | F |  |  | A | B | C | D | E | F
S1012 | SITE RETENTION ELEVATIONS - SHEET 2 | F |  |  | A | B | C | D | E | F
S1013 | SITE RETENTION ELEVATIONS - SHEET 3 | F |  |  | A | B | C | D | E | F
S1014 | SITE RETENTION ELEVATIONS - SHEET 4 | F |  |  | A | B | C | D | E | F
S1015 | SITE RETENTION ELEVATIONS - SHEET 5 | F |  |  | A | B | C | D | E | F
S1021 | TYPICAL SITE RETENTION DETAILS | E |  |  | A | B |  | C | D | E
S2000 | FOUNDATION LOADING PLAN - CORE LOADS - NOT USED | C |  |  |  | A |  |  | B | [5 empty] | C
S2001 | FOUNDATION LOADING PLAN - NOT USED | C |  |  |  | A |  |  | B | [5 empty] | C
S2002 | OVERALL FOUNDATION PLAN | C | [6 empty] | A | [5 empty] | B | C
S2011 | PILE LOADING PLAN | B | [6 empty] | A | [5 empty] | B
S2030 | TYPICAL SPREAD FOOTING DETAILS | B | [6 empty] | A | [5 empty] | B
S2040 | TYPICAL PILECAP & GROUND BEAM DETAILS - NOT USED | B | [6 empty] | A | [5 empty] | B
S2041 | RAFT FOUNDATION PLAN & SECTIONS - RF1 SHEET 1 | B | [6 empty] | A | [5 empty] | B
S2041.1 | RAFT FOUNDATION PLAN & SECTIONS - RF1 SHEET 2 | A | [12 empty] | A
S2042 | RAFT FOUNDATION PLAN & SECTIONS - RF2 SHEET 1 | A | [12 empty] | A
S2043 | RAFT FOUNDATION PLAN & SECTIONS RF3 - SHEET 1 | B | [6 empty] | A | [5 empty] | B
S2043.1 | RAFT FOUNDATION PLAN & SECTIONS RF3 - SHEET 2 | A | [12 empty] | A
S2044 | RAFT FOUNDATION PLAN & SECTIONS - RF4 SHEET 1 | B | [6 empty] | A | [5 empty] | B
S2044.1 | RAFT FOUNDATION PLAN & SECTIONS - RF4 SHEET 2 | A | [12 empty] | A
S2045 | RAFT FOUNDATION PLAN & SECTIONS - RF5 SHEET 1 | B | [6 empty] | A | [5 empty] | B
S2045.1 | RAFT FOUNDATION PLAN & SECTIONS - RF5 SHEET 2 | A | [12 empty] | A
S2046 | RAFT FOUNDATION PLAN & SECTIONS - RF6 & RF7 SHEET 1 | B | [6 empty] | A | [5 empty] | B
S2046.1 | RAFT FOUNDATION PLAN & SECTIONS RF6 & RF7 - SHEET 2 | A | [12 empty] | A
S2046.2 | RAFT FOUNDATION PLAN & SECTIONS RF6 & RF7 - SHEET 3 | A | [12 empty] | A
S2050 | STRAPPING BEAM SB-1 DETAIL - NOT USED | A | [12 empty] | A
S2060 | COMBINED FOOTING DETAILS 0- NOT USED | B | [12 empty] | A | B
S3001 | COLUMN SCHEDULE - SHEET 1 | -
S3002 | COLUMN SCHEDULE - SHEET 2 | -
S3003 | COLUMN SCHEDULE - SHEET 3 | -
S3020 | INSITU COLUMN DETAILS | A | [6 empty] | A
S3030 | PRECAST COLUMN DETAILS - SHEET 1 | A | [6 empty] | A
S3031 | PRECAST COLUMN DETAILS - SHEET 2 | A | [6 empty] | A
S4097 | BASEMENT 2 - OVERALL PLAN | I |  | A | B | C | D | E | F |  | G | H | I
S4098 | BASEMENT 1 - OVERALL PLAN | I |  | A | B | C | D | E | F |  | G | H | I
S4099 | GROUND LEVEL - OVERALL PLAN | J |  | A | B | C | D | E | F |  | G | H | I | J
S4100 | MEZZANINE LEVEL - OVERALL PLAN | I |  | A | B | C | D | E | F |  | G | H | I
S4101 | LEVEL 1 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4102 | LEVEL 2 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4103 | LEVEL 3 TO 5 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4106 | LEVEL 6 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4107 | LEVEL 7 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4108 | LEVEL 8 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4109 | LEVELS 9 AND 10 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4111 | LEVEL 11 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4112 | LEVEL 12 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4113 | LEVEL 13 - OVERALL PLAN | H |  | A | B | C | D | E | F |  |  | G | H
S4114 | LEVEL 14 - OVERALL PLAN | G |  | A | B | C | D | E | F |  |  |  | G
S4201 | BASEMENT 2 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4202 | BASEMENT 2 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4203 | BASEMENT 2 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4204 | BASEMENT 2 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4205 | BASEMENT 2 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4211 | BASEMENT 1 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4212 | BASEMENT 1 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4213 | BASEMENT 1 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4214 | BASEMENT 1 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4215 | BASEMENT 1 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4231 | GROUND - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4232 | GROUND - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4233 | GROUND - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4234 | GROUND - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4235 | GROUND - ZONE NE - GENERAL ARRANGEMENT PLAN | C |  |  |  |  | A |  | B |  |  |  |  | C
S4241 | MEZZANINE - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4242 | MEZZANINE - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4243 | MEZZANINE - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4244 | MEZZANINE - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4311 | LEVEL 1 - ZONE SW - GENERAL ARRANGEMENT PLAN | B |  |  |  |  | A |  | B
S4312 | LEVEL 1 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4313 | LEVEL 1 - ZONE SE - GENERAL ARRANGEMENT PLAN | B |  |  |  |  | A |  | B
S4314 | LEVEL 1 - ZONE E - GENERAL ARRANGEMENT PLAN | B |  |  |  |  | A |  | B
S4315 | LEVEL 1 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4321 | LEVEL 2 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4322 | LEVEL 2 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4323 | LEVEL 2 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4324 | LEVEL 2 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4325 | LEVEL 2 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4331 | LEVEL 3 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4332 | LEVEL 3 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4333 | LEVEL 3 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4334 | LEVEL 3 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4335 | LEVEL 3 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4341 | LEVEL 4 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4342 | LEVEL 4 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4343 | LEVEL 4 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4344 | LEVEL 4 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4345 | LEVEL 4 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4351 | LEVEL 5 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4352 | LEVEL 5 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4353 | LEVEL 5 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4354 | LEVEL 5 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4355 | LEVEL 5 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4361 | LEVEL 6 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4362 | LEVEL 6 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4363 | LEVEL 6 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4364 | LEVEL 6 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4365 | LEVEL 6 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4371 | LEVEL 7 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4372 | LEVEL 7 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4373 | LEVEL 7 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4374 | LEVEL 7 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4375 | LEVEL 7 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4381 | LEVEL 8 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4382 | LEVEL 8 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4383 | LEVEL 8 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4384 | LEVEL 8 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4385 | LEVEL 8 - ZONE NE - GENERAL ARRANGEMENT PLAN | B |  |  |  | A |  |  | B
S4391 | LEVEL 9 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4392 | LEVEL 9 - ZONE NW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4393 | LEVEL 9 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4394 | LEVEL 9 - ZONE E - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4395 | LEVEL 9 - ZONE NE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4401 | LEVEL 10 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4403 | LEVEL 10 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4411 | LEVEL 11 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4413 | LEVEL 11 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4421 | LEVEL 12 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4423 | LEVEL 12 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4431 | LEVEL 13 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4433 | LEVEL 13 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4441 | LEVEL 14 - ZONE SW - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4443 | LEVEL 14 - ZONE SE - GENERAL ARRANGEMENT PLAN | A | [6 empty] | A
S4911 | GROUND CONCRETE SECTIONS - SHEET 1 | A | [6 empty] | A
S4912 | GROUND CONCRETE SECTIONS - SHEET 2 | A | [6 empty] | A
S4921 | LEVEL 1 CONCRETE SECTIONS - SHEET 1 | A | [6 empty] | A
S4922 | LEVEL 1 CONCRETE SECTIONS - SHEET 2 | A | [6 empty] | A
S5001 | CORE WALL ELEVATIONS - SHEET 1 | B |  |  |  |  | A |  | B
S5002 | CORE WALL ELEVATIONS - SHEET 2 | B |  |  |  |  | A |  | B
S5003 | CORE WALL ELEVATIONS - SHEET 3 | B |  |  |  |  | A |  | B
S5004 | CORE WALL ELEVATIONS - SHEET 4 | B |  |  |  |  | A |  | B
S5005 | CORE WALL ELEVATIONS - SHEET 5 | B |  |  |  |  | A |  | B
S5006 | CORE WALL ELEVATIONS - SHEET 6 | B |  |  |  |  | A |  | B
S5007 | CORE WALL ELEVATIONS - SHEET 7 | B |  |  |  |  | A |  | B
S5008 | CORE WALL ELEVATIONS - SHEET 8 | B |  |  |  |  | A |  | B
S5009 | CORE WALL ELEVATIONS - SHEET 9 | B |  |  |  |  | A |  | B
S5010 | CORE WALL ELEVATIONS - SHEET 10 | C |  |  |  | A | B |  | C
S5011 | CORE WALL ELEVATIONS - SHEET 11 | B |  |  |  |  | A |  | B
S5012 | CORE WALL ELEVATIONS - SHEET 12 | B |  |  |  |  | A |  | B
S5021 | CORE WALL LAYOUTS - BUILDING NE | B |  |  |  |  | A |  | B
S5031 | CORE WALL LAYOUTS - BUILDING E | B |  |  |  |  | A |  | B
S5041 | CORE WALL LAYOUTS - BUILDING SE | B |  |  |  |  | A |  | B
S5051 | CORE WALL LAYOUTS - BUILDING SW | B |  |  |  |  | A |  | B
S5061 | CORE WALL LAYOUTS - BUILDING NW | B |  |  |  |  | A |  | B
S5101 | WALL ELEVATIONS - SHEET 1 | A | [6 empty] | A
S5102 | WALL ELEVATIONS - SHEET 2 | A | [6 empty] | A
S5103 | WALL ELEVATIONS - SHEET 3 | A | [6 empty] | A
S5104 | WALL ELEVATIONS - SHEET 4 | A | [6 empty] | A
S5105 | WALL ELEVATIONS - SHEET 5 | A | [6 empty] | A
S5106 | WALL ELEVATIONS - SHEET 6 | A | [6 empty] | A
S5107 | WALL ELEVATIONS - SHEET 7 | A | [6 empty] | A
S5108 | WALL ELEVATIONS - SHEET 8 | A | [6 empty] | A
S5109 | WALL ELEVATIONS - SHEET 9 | A | [6 empty] | A
S5110 | WALL ELEVATIONS - SHEET 10 | B |  |  |  |  | A |  | B
S5111 | WALL ELEVATIONS - SHEET 11 | A | [6 empty] | A
S5112 | WALL ELEVATIONS - SHEET 12 | A | [6 empty] | A
S5113 | WALL ELEVATIONS - SHEET 13 | A | [6 empty] | A
S5114 | WALL ELEVATIONS - SHEET 14 | A | [6 empty] | A
S5115 | WALL ELEVATIONS - SHEET 15 | A | [6 empty] | A
S5116 | WALL ELEVATIONS - SHEET 16 | A | [6 empty] | A
S5117 | WALL ELEVATIONS - SHEET 17 | A | [6 empty] | A
S5118 | WALL ELEVATIONS - SHEET 18 | A | [6 empty] | A
S5119 | WALL ELEVATIONS - SHEET 19 | A | [6 empty] | A
S5201 | FACADE ELEVATIONS - SHEET 1 | D |  |  |  | A | B | C | D
S5202 | FACADE ELEVATIONS - SHEET 2 | D |  |  |  | A | B | C | D
S5203 | FACADE ELEVATIONS - SHEET 3 | D |  |  |  | A | B | C | D
S5204 | FACADE ELEVATIONS - SHEET 4 | D |  |  |  | A | B | C | D
S5205 | FACADE ELEVATIONS - SHEET 5 | D |  |  |  | A | B | C | D
S5206 | FACADE ELEVATIONS - SHEET 6 | D |  |  |  | A | B | C | D
S5207 | FACADE ELEVATIONS - SHEET 7 | D |  |  |  | A | B | C | D
S5208 | FACADE ELEVATIONS - SHEET 8 | D |  |  |  | A | B | C | D
S5209 | FACADE ELEVATIONS - SHEET 9 | D |  |  |  | A | B | C | D
S5210 | FACADE ELEVATIONS - SHEET 10 | D |  |  |  | A | B | C | D
S5211 | FACADE ELEVATIONS - SHEET 11 | D |  |  |  | A | B | C | D
S5212 | FACADE ELEVATIONS - SHEET 12 | D |  |  |  | A | B | C | D
S5213 | FACADE ELEVATIONS - SHEET 13 | D |  |  |  | A | B | C | D
S5301 | FACADE SECTIONS - SHEET 1 | D |  |  |  | A | B | C | D
S5302 | FACADE SECTIONS - SHEET 2 | D |  |  |  | A | B | C | D
S7000 | HEADER BEAM DETAILS | A | [6 empty] | A
S7001 | HEADER BEAM PENO DETAILS | A | [6 empty] | A
S7100 | TYPICAL INSITU WALL DETAILS | B | A | [5 empty] | B
S7200 | TYPICAL PRECAST DETAILS - SHEET 1 | A | [6 empty] | A
S7201 | TYPICAL PRECAST DETAILS - SHEET 2 | A | [6 empty] | A
S7210 | PRECAST WET JOINT DETAILS | A | [6 empty] | A
S7300 | SLAB ON GROUND DETAILS | A | [6 empty] | A
S7400 | TYPICAL CONCRETE DETAILS - SHEET 1 | A | [6 empty] | A
S7401 | TYPICAL CONCRETE DETAILS - SHEET 2 | A | [6 empty] | A
S7500 | TYPICAL CONCRETE STAIR DETAILS | A | [6 empty] | A
S7501 | FEATURE STAIR CONCRETE DETAIL | A | [6 empty] | A
S7502 | FEATURE STAIR DETAIL - SHEET 2 | A | [6 empty] | A
S7600 | TYPICAL BLOCKWORK DETAILS - SHEET 1 | A | [6 empty] | A
S7601 | TYPICAL BLOCKWORK DETAILS - SHEET 2 | A | [6 empty] | A
S8001 | GROUND LEVEL STEELWORKS - SHEET 1 | A | [6 empty] | A
S8011 | LEVEL 1 STEELWORKS | A | [6 empty] | A
S8071 | LEVEL 7 STEELWORKS - SHEET 1 | A | [6 empty] | A
S8072 | LEVEL 7 STEELWORKS - SHEET 2 | A | [6 empty] | A
S8111 | LEVEL 11 STEELWORKS | A | [6 empty] | A
S8201 | FACADE STEELWORKS - BUILDING E EAST ELEVATION | A | [6 empty] | A
SX1022 | SITE RETENTION DETAILS - SHEET 1 | A |  |  |  | A
SX1023 | SITE RETENTION DETAILS - SHEET 2 | A |  |  |  | A
SX1031 | SITE RETENTION SECTIONS & DETAILS - SHEET 1 | -
SX2030A | TYPICAL SPREAD FOOTINGS DETAILS | -
SX2040A | TYPICAL PILECAP & GROUND BEAM DETAILS | -
SX3011 | COLUMN TRANSITION DETAILS | -
SX6001 | TRANSFER WALL ELEVATIONS & DETAILS - SHEET 1 | -
SX6002 | TRANSFER WALL ELEVATIONS & DETAILS - SHEET 2 | -
SX7000A | HEADER BEAM DETAILS | -
SX7010 | BOUNDARY ELEMENT DETAILS | -
SX7200B | TYPICAL PRECAST DETAILS - SHEET 1 | -
SX7300A | HYDROSTATIC SLAB ON GROUND DETAILS | -
Sxx | CAPPING BEAM PLAN | -